## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 1 | Mahesh | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Aswin | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Sowrabh Kumar | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Elzabeth | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Praveen Eswar | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 1 | Surya | DevOps Engineer | Week 1 | No

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
1 | Understood cloud computing basics and why cloud is used. | 2026-05-06 | 2026-05-07 | We explored the fundamentals of cloud computing, understood and compared the architectural differences between AWS and Azure
2 | Explored Azure networking, public IP allocation, DHCP, and VM connectivity. | 2026-05-08 | 2026-05-09 | Created a public VM in Azure using both UI and Terraform and exposed a simple application to the internet, and understood DHCP and public IP allocation.
3 | Explored Azure VNet, network architecture, and Bastion host. | 2026-05-11 | 2026-05-12 | Built a custom network in Azure with RG, VNet, subnets, and VMs, exposed a private subnet app using a load balancer (UI + Terraform), and accessed private VM using Azure Bastion.
4 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | 2026-05-13 | 2026-05-14 | Explored the implementation of VNet peering within the same Azure subscription to enable secure and low-latency communication between virtual networks over Microsoft’s private backbone infrastructure.
5 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | 2026-05-15 | 2026-05-16 | Explored hybrid cloud networking by establishing secure connectivity between on-premises infrastructure and Azure virtual networks using Site-to-Site VPN Gateway.
6 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | 2026-05-18 | 2026-05-19 | Explored Azure Virtual Machine Scale Sets (VMSS) to implement scalable and highly available application infrastructure.
7 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | 2026-05-20 | 2026-05-21 | Learned about Microsoft Azure Application Gateway, WAF, and the differences between Layer 4 and Layer 7 load balancers. Understood how traffic routing and application security work in cloud-based architectures.
8 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | 2026-05-21 | 2026-05-22 | Created and configured Microsoft Azure Application Gateway and deployed two applications behind it. Successfully implemented both host-based routing and path-based routing for directing traffic to the appropriate backend applications.
9 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | 2026-05-25 | 2026-05-26 | Discussed the pain points and management challenges of on-premises cluster environments and explored the benefits of AKS in Microsoft Azure. Created an AKS cluster and successfully deployed an application using Kubernetes YAML configuration files.
10 | Azure Database Management | 2026-05-27 | 2026-05-28 | Understood Azure Database management and configured managed database capabilities with secure access, backup, monitoring, and performance considerations.
11 | Azure App Services, Azure Front Door | 2026-05-29 | 2026-05-30 | Deployed and configured applications on Azure App Service with app settings, scaling options, deployment workflow, and monitoring. Configured Azure Front Door concepts for secure global routing, frontend/backend mapping, health probes, and edge protection.
12 | Azure Storage Account, Azure Blob Storage | 2026-06-01 | 2026-06-02 | Created and reviewed Azure Storage Account settings for secure access, redundancy, private/public connectivity, and data protection. Configured Blob Storage containers with access tiers, secure access patterns, upload/download flow, and lifecycle management.
13 | Azure Function, Azure Entra ID | 2026-06-03 | 2026-06-03 | Created and understood serverless Azure Function workflows with triggers, bindings, configuration, and execution monitoring. Configured and reviewed Azure Entra ID identity features including user/group management, app registration, RBAC, and secure authentication.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
1 | Team1 | T1-001 | Understood cloud computing basics and why cloud is used. | Mahesh | 5 | Done
1 | Team1 | T1-002 | Understood cloud computing basics and why cloud is used. | Aswin | 5 | Done |  | Backlog
1 | Team1 | T1-003 | Understood cloud computing basics and why cloud is used. | Sowrabh Kumar | 5 | Done
1 | Team1 | T1-004 | Understood cloud computing basics and why cloud is used. | Elzabeth | 5 | Done |  | To Do
1 | Team1 | T1-005 | Understood cloud computing basics and why cloud is used. | Praveen Eswar | 5 | Done
1 | Team1 | T1-006 | Understood cloud computing basics and why cloud is used. | Surya | 5 | Done |  | In Progress
2 | Team1 | T1-007 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Mahesh | 4 | Done
2 | Team1 | T1-008 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Aswin | 4 | Done |  | Code Review
2 | Team1 | T1-009 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Sowrabh Kumar | 4 | Done
2 | Team1 | T1-010 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Elzabeth | 4 | Done |  | Done
2 | Team1 | T1-011 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Praveen Eswar | 4 | Done
2 | Team1 | T1-012 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Surya | 4 | Done |  | Blocked
3 | Team1 | T1-013 | Understood Azure networking with VNet, architecture, and Bastion host. | Mahesh | 4 | Done
3 | Team1 | T1-014 | Understood Azure networking with VNet, architecture, and Bastion host. | Aswin | 4 | Done
3 | Team1 | T1-015 | Understood Azure networking with VNet, architecture, and Bastion host. | Sowrabh Kumar | 4 | Done
3 | Team1 | T1-016 | Understood Azure networking with VNet, architecture, and Bastion host. | Elzabeth | 4 | Done
3 | Team1 | T1-017 | Understood Azure networking with VNet, architecture, and Bastion host. | Praveen Eswar | 4 | Done
3 | Team1 | T1-018 | Understood Azure networking with VNet, architecture, and Bastion host. | Surya | 4 | Done
4 | Team1 | T1-019 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Mahesh | 4 | Done
4 | Team1 | T1-020 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Aswin | 4 | Done
4 | Team1 | T1-021 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Sowrabh Kumar | 4 | Done
4 | Team1 | T1-022 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Elzabeth | 4 | Done
4 | Team1 | T1-023 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Praveen Eswar | 4 | Done
4 | Team1 | T1-024 | Intra-Subscription Azure VNet Peering Architecture, Cross-Cloud Connectivity Between AWS and Microsoft Azure | Surya | 4 | Done
5 | Team1 | T1-025 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Mahesh | 5 | Done
5 | Team1 | T1-026 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Aswin | 5 | Done
5 | Team1 | T1-027 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Sowrabh Kumar | 5 | Done
5 | Team1 | T1-028 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Elzabeth | 5 | Done
5 | Team1 | T1-029 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Praveen Eswar | 5 | Done
5 | Team1 | T1-030 | Hybrid Cloud Connectivity Between On-Premises Infrastructure and Azure Cloud, Site-to-Site VPN Connectivity Using Azure VPN Gateway | Surya | 5 | Done
6 | Team1 | T1-031 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Mahesh | 5 | Done
6 | Team1 | T1-032 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Aswin | 5 | Done
6 | Team1 | T1-033 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Sowrabh Kumar | 5 | Done
6 | Team1 | T1-034 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Elzabeth | 5 | Done
6 | Team1 | T1-035 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Praveen Eswar | 5 | Done
6 | Team1 | T1-036 | Azure Virtual Machine Scale Sets (VMSS) for Auto Scaling and High Availability | Surya | 5 | Done
7 | Team1 | T1-037 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Mahesh | 4 | Done
7 | Team1 | T1-038 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Aswin | 4 | Done
7 | Team1 | T1-039 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Sowrabh Kumar | 4 | Done
7 | Team1 | T1-040 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Elzabeth | 4 | Done
7 | Team1 | T1-041 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Praveen Eswar | 4 | Done
7 | Team1 | T1-042 | Explore Azure Application Gateway, WAF, and Layer 4 vs Layer 7 Load Balancing concepts for secure and scalable application architecture design. | Surya | 4 | Done
8 | Team1 | T1-043 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Mahesh | 5 | Done
8 | Team1 | T1-044 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Aswin | 5 | Done
8 | Team1 | T1-045 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Sowrabh Kumar | 5 | Done
8 | Team1 | T1-046 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Elzabeth | 5 | Done
8 | Team1 | T1-047 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Praveen Eswar | 5 | Done
8 | Team1 | T1-048 | Implement and configure Azure Application Gateway routing for multiple applications using host-based and path-based routing. | Surya | 5 | Done
9 | Team1 | T1-049 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Mahesh | 4 | Done
9 | Team1 | T1-050 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Aswin | 4 | Done
9 | Team1 | T1-051 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Sowrabh Kumar | 4 | Done
9 | Team1 | T1-052 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Elzabeth | 4 | Done
9 | Team1 | T1-053 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Praveen Eswar | 4 | Done
9 | Team1 | T1-054 | Understand the limitations of on-premises clusters and explore application deployment in AKS using Kubernetes manifests. | Surya | 4 | Done
10 | Team1 | T1-055 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Mahesh | 5 | Done
10 | Team1 | T1-056 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Aswin | 5 | Done
10 | Team1 | T1-057 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Sowrabh Kumar | 5 | Done
10 | Team1 | T1-058 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Elzabeth | 5 | Done
10 | Team1 | T1-059 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Praveen Eswar | 5 | Done
10 | Team1 | T1-060 | Explored Azure Database management concepts including provisioning, connectivity, backups, scaling, monitoring, and security for managed database services. | Surya | 5 | Done
11 | Team1 | T1-061 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Mahesh | 5 | Done
11 | Team1 | T1-062 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Aswin | 5 | Done
11 | Team1 | T1-063 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Sowrabh Kumar | 5 | Done
11 | Team1 | T1-064 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Elzabeth | 5 | Done
11 | Team1 | T1-065 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Praveen Eswar | 5 | Done
11 | Team1 | T1-066 | Explored Azure App Service for hosting web applications and APIs with deployment slots, configuration, scaling, and monitoring. | Surya | 5 | Done
11 | Team1 | T1-067 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Mahesh | 4 | Done
11 | Team1 | T1-068 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Aswin | 4 | Done
11 | Team1 | T1-069 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Sowrabh Kumar | 4 | Done
11 | Team1 | T1-070 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Elzabeth | 4 | Done
11 | Team1 | T1-071 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Praveen Eswar | 4 | Done
11 | Team1 | T1-072 | Explored Azure Front Door for global application delivery, routing, SSL termination, WAF integration, and high availability. | Surya | 4 | Done
12 | Team1 | T1-073 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Mahesh | 4 | Done
12 | Team1 | T1-074 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Aswin | 4 | Done
12 | Team1 | T1-075 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Sowrabh Kumar | 4 | Done
12 | Team1 | T1-076 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Elzabeth | 4 | Done
12 | Team1 | T1-077 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Praveen Eswar | 4 | Done
12 | Team1 | T1-078 | Explored Azure Storage Account configuration including redundancy, access control, networking, encryption, and lifecycle management. | Surya | 4 | Done
12 | Team1 | T1-079 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Mahesh | 4 | Done
12 | Team1 | T1-080 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Aswin | 4 | Done
12 | Team1 | T1-081 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Sowrabh Kumar | 4 | Done
12 | Team1 | T1-082 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Elzabeth | 4 | Done
12 | Team1 | T1-083 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Praveen Eswar | 4 | Done
12 | Team1 | T1-084 | Explored Azure Blob Storage for object storage, containers, access tiers, SAS access, lifecycle rules, and secure uploads. | Surya | 4 | Done
13 | Team1 | T1-085 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Mahesh | 5 | Done
13 | Team1 | T1-086 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Aswin | 5 | Done
13 | Team1 | T1-087 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Sowrabh Kumar | 5 | Done
13 | Team1 | T1-088 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Elzabeth | 5 | Done
13 | Team1 | T1-089 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Praveen Eswar | 5 | Done
13 | Team1 | T1-090 | Explored Azure Functions for serverless execution using triggers, bindings, application settings, monitoring, and deployment. | Surya | 5 | Done
13 | Team1 | T1-091 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Mahesh | 5 | Done
13 | Team1 | T1-092 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Aswin | 5 | Done
13 | Team1 | T1-093 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Sowrabh Kumar | 5 | Done
13 | Team1 | T1-094 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Elzabeth | 5 | Done
13 | Team1 | T1-095 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Praveen Eswar | 5 | Done
13 | Team1 | T1-096 | Explored Azure Entra ID for identity management, users, groups, app registrations, role-based access, and authentication flows. | Surya | 5 | Done

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -